# TargetAI Phase 1 Action Plan

Counselor Credibility Pilot (Months 0-2)

Confidential | December 2025

# Executive Summary

This document provides detailed, week-by-week action plans for Phase 1 of TargetAI's go-to-market strategy. The goal is to onboard 10-20 carefully selected independent counselors during the summer months (May-August) to validate product-market fit and build organic credibility within the counseling community.

# 1. Outreach Strategy

The outreach strategy is founder-led and highly personalized. The goal is quality over quantity—building genuine relationships with counselors who can become long-term advocates.

## 1.1 Channel Strategy

Primary Channels (70% of effort)

### LinkedIn Direct Outreach

- Target: Independent Educational Consultants (IECs) with 500+ connections

- Look for: IECA members, former admissions officers, counselors with active content

- Approach: Connect first, engage with their content for 1-2 weeks, then personalized message

- Expected response rate: 15-25% with warm approach

### Professional Association Networks

- IECA (Independent Educational Consultants Association) - Primary target

- HECA (Higher Education Consultants Association) - Secondary target

- NACAC regional affiliates - for geographic diversity

- Strategy: Attend virtual events, participate in forums, identify thought leaders

Secondary Channels (30% of effort)

### Warm Introductions

- Leverage StemPro Academy existing network

- Ask early adopters for 2-3 referrals each

- Target: Counselors they respect but who aren't direct competitors

### Content-Based Attraction

- Publish 2-3 thought leadership pieces on LinkedIn about AI in counseling

- Focus on ethical AI use—align with TargetAI positioning

- Include soft CTA: "DM me if you'd like early access to what we're building"

## 1.2 Messaging Framework

Initial Connection Message (LinkedIn)

Hi [Name],

I've been following your work on [specific post/topic]. Your perspective on [specific insight] really resonated with me.

I'm building a counselor-first AI platform at StemPro Academy—designed to amplify your expertise, not replace it. No AI essay writing. No acceptance guarantees. Just intelligent tools that save you time on admin so you can focus on what matters.

Would you be open to a 20-minute call? I'd love your perspective—even if it's just to tell me what we're getting wrong.

— [Your name]

Follow-Up Message (After Demo Interest)

Thanks for your interest, [Name]!

Quick context: We're in private pilot mode with just 10-15 counselors. The goal is to get this right before going broader—your feedback will directly shape the product.

Pilot includes: Full platform access, priority support, and a founding member rate locked in forever.

Here's my calendar: [link]. Pick any time that works.

## 1.3 Weekly Outreach Cadence

| Week | Outreach Volume | Focus Activities | Target Outcome |
| --- | --- | --- | --- |
| 1-2 | 20 connections/week | LinkedIn profile optimization, initial connects | 40 new connections |
| 3-4 | 15 DMs/week | Personalized outreach to engaged connections | 8-10 demo calls scheduled |
| 5-6 | 10 DMs/week + referral asks | Demos, onboarding, referral requests | 5-8 pilots started, 10+ referrals |
| 7-8 | Referral-focused | Support existing pilots, pursue referrals | 10-15 total active pilots |

# 2. Pilot Counselor Selection Criteria

Not all counselors are equal for a pilot. The right mix ensures diverse feedback, strong advocacy potential, and representative use cases.

## 2.1 Must-Have Criteria

Every pilot counselor should meet ALL of these requirements:

- Active Caseload: Currently working with 10+ students annually. This ensures they have real workflow needs and can stress-test the platform.

- Tech Comfort: Already uses digital tools (CRM, Zoom, Google Workspace). Not looking to convert tech-resistant counselors in pilot phase.

- Independent or Small Firm: Solo practitioners or firms with <5 counselors. Large organizations have slower decision cycles and complex procurement.

- Ethical Alignment: Values integrity in the admissions process. Red flag: counselors who promise outcomes or use aggressive marketing.

- Feedback Willingness: Explicitly agrees to provide structured feedback (bi-weekly check-ins, NPS survey, exit interview).

## 2.2 Preferred Attributes (Aim for Diversity)

Build a pilot cohort that represents different use cases:

| Attribute | Target Mix | Why It Matters |
| --- | --- | --- |
| Experience Level | 5 newer (<5 yrs), 10 veteran (5+ yrs) | Different workflow needs and tech expectations |
| Geographic Region | Mix of coasts, midwest, south | Regional differences in college prep culture |
| Student Demographics | Mix: affluent, middle-income, scholarship-focused | Tests platform across different use cases |
| Specialization | General IECs + 3-4 specialists (STEM, arts, athletes) | Validates niche applicability |
| Social Presence | At least 5 with 1,000+ LinkedIn followers | Potential advocates with reach |

## 2.3 Red Flags (Disqualifiers)

Do NOT onboard counselors who:

- Make outcome guarantees ("Get into your dream school!")

- Have negative industry reputation or ethical complaints

- Are direct competitors building similar tools

- Won't commit to feedback schedule (too busy = not a good pilot fit)

- Express hostility toward AI in counseling (not skepticism—hostility)

## 2.4 Scoring Rubric

Use this scorecard during initial calls to qualify candidates:

| Criterion | 1 pt | 2 pts | 3 pts | Notes |
| --- | --- | --- | --- | --- |
| Active caseload size | 10-20 | 20-40 | 40+ |  |
| Current tech stack sophistication | Basic | Moderate | Advanced |  |
| Feedback commitment level | Monthly | Bi-weekly | Weekly |  |
| Industry influence/reach | Low | Medium | High |  |
| Ethical alignment signals | Unclear | Aligned | Champion |  |

Minimum score to proceed: 8/15. Prioritize candidates scoring 12+ for first wave.

# 3. Onboarding & Demo Process

A structured onboarding process ensures counselors reach value quickly and stay engaged throughout the pilot.

## 3.1 Onboarding Timeline Overview

| Phase | Duration | Key Activities |
| --- | --- | --- |
| Discovery Call | 20-30 minutes | Qualify fit, understand workflow, gauge interest |
| Demo Session | 45-60 minutes | Full platform walkthrough, Q&A, pilot agreement |
| Hands-on Setup | 30-45 minutes | Account creation, first student import, quick wins |
| Week 1 Check-in | 15-20 minutes | Troubleshoot issues, answer questions, gather feedback |
| Bi-weekly Syncs | 15 minutes ongoing | Progress check, feature feedback, NPS pulse |

## 3.2 Discovery Call Script

Purpose: Qualify the counselor and understand their specific needs before investing in a full demo.

Opening (2 min)

"Thanks for taking the time, [Name]. Before I tell you about what we're building, I'd love to understand your practice better. This helps me know if we'd actually be useful to you—I'd rather be honest upfront than waste your time."

Discovery Questions (10-15 min)

- "Walk me through a typical week during peak season. Where do you spend most of your time?"

- "What tools do you currently use to manage students and track applications?"

- "How do you currently handle meeting notes and follow-ups?"

- "What's your biggest pain point—the thing that makes you think 'there has to be a better way'?"

- "How do you feel about AI in counseling? What excites you or concerns you?"

Brief Pitch (5 min)

"Based on what you've shared, here's where I think TargetAI could help: [customize to their pain points]. We're specifically built for counselors—not students, not parents. The AI assists you; it doesn't replace your judgment. And we have a hard rule: no AI essay writing, no acceptance guarantees."

Close & Next Steps (3 min)

"I'd love to show you the platform in action. I can do a 45-minute demo where you'll see exactly how this works with your workflow. Would [date/time] work for you?"

## 3.3 Demo Session Structure

Duration: 45-60 minutes

Demo Flow:

| Time | Section | Details |
| --- | --- | --- |
| 0-5 min | Reconnect & Agenda | Recap pain points from discovery call, set expectations |
| 5-15 min | Student Management Demo | Show dashboard, add student flow, profile completion tracking |
| 15-25 min | AI Features Showcase | AI chat assistant, meeting reports, college gap analysis |
| 25-35 min | Essay & College Tools | Essay positioning map, college list builder, compare students |
| 35-45 min | Q&A + Pilot Discussion | Answer questions, discuss pilot terms, secure commitment |
| 45-60 min | (Optional) Live Setup | If ready to commit, begin hands-on setup immediately |

## 3.4 Hands-On Setup Session

Goal: Get the counselor to "first value" within this session—they should leave with a real student in the system and one AI-generated insight.

Setup Checklist:

- Account Creation (5 min) - Create counselor account, set preferences

- First Student Import (10 min) - Add 1-2 real students (with consent) or demo students

- Profile Completion (10 min) - Fill in key profile sections for one student

- AI Quick Win (10 min) - Generate a profile summary or college suggestions using AI chat

- Schedule First Meeting (5 min) - Create a meeting in the system to test meeting features

## 3.5 Ongoing Support Structure

| Support Type | Frequency | Format |
| --- | --- | --- |
| Bi-weekly check-in | Every 2 weeks | 15-min video call or async Loom |
| Slack/Email support | Ongoing | Response within 4 hours during business days |
| Bug/feedback submission | As needed | In-app feedback button or direct message |
| Feature request review | Monthly | Compiled list shared with pilot cohort |
| NPS survey | Week 4 and Week 8 | Simple 1-question survey + optional comments |

## 3.6 Pilot Agreement Terms

What the counselor agrees to:

- Use TargetAI with at least 5 students during the pilot period

- Participate in bi-weekly check-in calls (15 minutes)

- Complete NPS surveys at Week 4 and Week 8

- Provide honest feedback on bugs, UX issues, and feature requests

- Keep platform details confidential during private pilot

What TargetAI provides:

- Free access during pilot period (8 weeks)

- Founding member pricing locked in: 50% off standard rates, forever

- Priority support with direct founder access

- Early access to new features

- Recognition as a founding partner (optional, with consent)

# Appendix: Weekly Execution Checklist

## Week 1-2: Foundation

- Optimize LinkedIn profile with counselor-focused positioning

- Build target list of 50 counselors matching selection criteria

- Send 20 connection requests with personalized notes

- Engage with 10 counselor posts (meaningful comments, not generic)

- Draft and publish first LinkedIn thought leadership post

- Prepare demo environment with realistic sample data

## Week 3-4: Active Outreach

- Send 15 personalized DMs to engaged connections

- Schedule 8-10 discovery calls

- Conduct discovery calls using provided script

- Score candidates using rubric

- Convert qualified leads to demo sessions

- Publish second thought leadership post

## Week 5-6: Conversion & Onboarding

- Conduct demo sessions for qualified candidates

- Complete hands-on setup for committed pilots

- Execute Week 1 check-in calls with new pilots

- Ask each pilot for 2-3 referrals

- Document feedback and feature requests

- Continue outreach via referrals

## Week 7-8: Scale & Validate

- Reach 10-15 active pilot counselors

- Conduct bi-weekly check-ins with all pilots

- Deploy Week 4 NPS survey

- Analyze feedback themes and prioritize fixes

- Identify 3-5 potential advocate counselors

- Begin Phase 2 planning with validated learnings

# Success Metrics Summary

| Metric | Target | Measurement Method |
| --- | --- | --- |
| Pilot counselors onboarded | 10-15 | CRM tracking |
| Net Promoter Score | ≥ 8 (promoter threshold) | NPS survey at Week 4 & 8 |
| Weekly active usage | ≥ 70% of pilots | Platform analytics |
| Referrals generated | 10+ qualified referrals | Referral tracking |
| Feature feedback items | 30+ actionable items | Feedback log |
| Positioning language validated | 3+ resonant phrases | Qualitative interviews |

— End of Document —

TargetAI by StemPro Academy | Confidential